## GANTT
Automobile Accident Study
Week of
| Due Date | Role | Owner (graded parties) | Status | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-03-29 | 2020-04-05 | 2020-04-12 | 2020-04-19
Project Proposal | 2020-02-28 | Team | Team | In process
Data Phase
Obtain and clean accident data | 2020-03-04 | Individual |  | Not Started
Obtain and clean weather data | 2020-03-04 | Individual |  | Not Started
Create combined dataset grouped by day | 2020-03-07 | Individual |  | Not Started
Initial Analysis Phase
Individual Dataset Visualizations | 2020-03-14 | Individual |  | Not Started
Individual Dataset Interpretations | 2020-03-14 | Individual |  | Not Started
Combined Dataset Visualizations | 2020-03-14 | Individual |  | Not Started
Combined Dataset Interpretations | 2020-03-14 | Individual |  | Not Started
Correlation Visualizations | 2020-03-21 | Individual
Correlation Interpretation | 2020-03-21 | Individual |  | Not Started
Model Creation Phase
Linear Regression Creation | 2020-03-28 | Individual |  | Not Started
Linear Regression Interpretation | 2020-03-28 | Individual |  | Not Started
Decision Tree Creation | 2020-04-04 | Individual |  | Not Started
Decision Tree Interpretation | 2020-04-04 | Individual |  | Not Started
Finalization Phase
Finalize Project | 2020-04-11 | Individual |  | Not Started
Finalize Presentation / Record Video | 2020-04-18 | Individual |  | Not Started